## Explanation
This spreadsheet is filled out to with example data illustrate what is required.
You will modify this for your use.
Please notice that both have line items broken out by work type.
The Paid Items List, PIL, is sometimes referred to as the Bid Item List.
This is submitted with the contract documents after letting.
The Final Paid Items List, FPIL, is created throughout the project, or at the end,
accounting for any and all change orders.
All non-participating items need to be marked as such.
Be sure to use formulas in the total column on the PIL.
And formulas in the Change Order and Rev. Total columns on the FPIL.
If you have any questions or concerns, please feel free to contact
Alison Bell at 785-207-5124.

## PIL
Project Description
KDOT Project No.
Date
No. | Description | Unit | Quantity | Unit Price | Total
1 | Mobilization | LS | 1 | 40000 | 40000
2 | Clearing & Grubbing | LS | 1 | 2000 | 2000
3 | Removal of Existing Structures | LS | 1 | 17000 | 17000
4 | Contractor Construction Staking | LS | 1 | 2400 | 2400
5 | Project Sign (Non-Participating) | EA | 2 | 1000 | 2000
6 | Grading & Compaction | LS | 1 | 47000 | 47000
7 | Erosion Control | LS | 1 | 3200 | 3200
8 | 6" Asphaltic Commercial BM-2 | SY | 1436 | 23 | 33028
9 | Portland Cement Concrete Pavement (11" Uniform)(A.E.) | SY | 112 | 70 | 7840
10 | 2" Asphaltic Concrete Surface | SY | 22 | 65 | 1430
11 | 7" Asphlatic Concrete Base | SY | 22 | 200 | 4400
12 | Granular Base (4") | SY | 112 | 15 | 1680
13 | Type B Curb and Gutter | LF | 1023 | 20 | 20460
14 | Type A Sidewalk Ramp | EA | 2 | 1500 | 3000
15 | Type B Sidewalk Ramp | EA | 1 | 2700 | 2700
16 | 6" Concrete Walkway (Island) | SY | 62 | 70 | 4340
17 | Detectable Warning Pavers (Island) | SF | 64 | 20 | 1280
18 | Concrete Median Nose | EA | 1 | 1000 | 1000
19 | Seeding | ACRE | 0.75 | 2150 | 1612.5
20 | Pedestrian Bridge Fence | LF | 390 | 111 | 43290
21 | Handrail | LF | 367 | 96 | 35232
22 | 6'x4' Curb Inlet | EA | 1 | 3800 | 3800
23 | 6'x5' Curb Inlet | EA | 1 | 4100 | 4100
24 | 2.5' x 4.0' Ellip. RCP | LF | 35 | 115 | 4025
25 | Reuse 2.5' x 4.0' Ellip. RCP Flared End Section | EA | 2 | 150 | 300
26 | 30" RCP | LF | 69 | 130 | 8970
27 | 36" Storm Pipe | LF | 62 | 70 | 4340
28 | 36" End Section | EA | 1 | 1300 | 1300
29 | 2' x 2' Grate Inlet Top Replacement | EA | 1 | 1500 | 1500
30 | Concrete Flume | SY | 12 | 90 | 1080
31 | Concrete Collar | EA | 1 | 1600 | 1600
32 | 24" Riprap | SY | 82 | 60 | 4920
33 | Traffic Signal Modification-95th Street & Legler/I-435 | LS | 1 | 14000 | 14000
34 | Traffic Signal Modification-95th Street & Ridge | LS | 1 | 4000 | 4000
35 | 4" Solid White Lane Line (Thermo) | LF | 138 | 2 | 276
35a | 4" Solid White Lane Line (Epoxy) | lf | 138 | 13.75
36 | 12" Solid White Crosswalk Line (Thermo) | LF | 175 | 10 | 1750
36a | 12" solid white Crosswalk Line (Epoxy) | lf | 175 | 16.5
37 | 24" Solid White Stop Line (Thermo) | LF | 15 | 13 | 195
37a | 24" solid White Stop Line (Epoxy) | lf | 15 | 22
38 | Remove and Reset Existing Signs | EA | 5 | 350 | 1750
39 | Traffic Control | LS | 1 | 8000 | 8000
40 | 40' Aluminum Pole (w/ 12' Arm & 400w Cobrahead) | EA | 9 | 3500 | 31500
41 | 3-1c No. 4 Type USE Distribution Cable | LF | 6900 | 1.75 | 12075
42 | Type I Junction Box | EA | 3 | 400 | 1200
43 | Street Lighting Conduit - 2" | LF | 1900 | 6 | 11400
44 | Relocate Light Pole | EA | 1 | 2000 | 2000
|  |  |  | TOTAL | 398973.5
Work Type Summary
Non-Participating
|  |  |  | Roadway | 2000
Participating
|  |  |  | Common Items | 42000
|  |  |  | Roadway | 210073.5 | 398973.5
|  |  |  | Surfacing | 48378
|  |  |  | Bridges | 78522
|  |  |  | Traffic Signals | 18000
|  |  |  | TOTAL | 398973.5

## FPIL
Project Description
KDOT Project No.
Date
No. | Description | Unit | Quantity | Unit Price | Total | CO 1 | CO 2 | CO 3 | New total
1 | Mobilization | LS | 1 | 40000 | 40000 |  |  |  | 40000
2 | Clearing & Grubbing | LS | 1 | 2000 | 2000 |  |  |  | 2000
3 | Removal of Existing Structures | LS | 1 | 17000 | 17000 |  |  |  | 17000
4 | Contractor Construction Staking | LS | 1 | 2400 | 2400 |  |  |  | 2400
5 | Project Sign (Non-Participating) | EA | 2 | 1000 | 2000 |  |  |  | 2000
6 | Grading & Compaction | LS | 1 | 47000 | 47000 |  |  |  | 47000
7 | Erosion Control | LS | 1 | 3200 | 3200 |  |  |  | 3200
8 | 6" Asphaltic Commercial BM-2 | SY | 1436 | 23 | 33028 |  |  |  | 33028
9 | Portland Cement Concrete Pavement (11" Uniform)(A.E.) | SY | 112 | 70 | 7840 |  |  |  | 7840
10 | 2" Asphaltic Concrete Surface | SY | 22 | 65 | 1430 | -1430 |  |  | 0
11 | 7" Asphlatic Concrete Base | SY | 22 | 200 | 4400 | -4400 |  |  | 0
12 | Granular Base (4") | SY | 112 | 15 | 1680 |  |  |  | 1680
13 | Type B Curb and Gutter | LF | 1023 | 20 | 20460 |  |  |  | 20460
14 | Type A Sidewalk Ramp | EA | 2 | 1500 | 3000 |  |  |  | 3000
15 | Type B Sidewalk Ramp | EA | 1 | 2700 | 2700 |  |  |  | 2700
16 | 6" Concrete Walkway (Island) | SY | 62 | 70 | 4340 |  |  |  | 4340
17 | Detectable Warning Pavers (Island) | SF | 64 | 20 | 1280 |  |  |  | 1280
18 | Concrete Median Nose | EA | 1 | 1000 | 1000 |  |  |  | 1000
19 | Seeding | ACRE | 0.75 | 2150 | 1612.5 |  | -795.5 |  | 817
20 | Pedestrian Bridge Fence | LF | 390 | 111 | 43290 |  |  |  | 43290
21 | Handrail | LF | 367 | 96 | 35232 |  |  |  | 35232
22 | 6'x4' Curb Inlet | EA | 1 | 3800 | 3800 |  |  |  | 3800
23 | 6'x5' Curb Inlet | EA | 1 | 4100 | 4100 |  |  |  | 4100
24 | 2.5' x 4.0' Ellip. RCP | LF | 35 | 115 | 4025 |  |  |  | 4025
25 | Reuse 2.5' x 4.0' Ellip. RCP Flared End Section | EA | 2 | 150 | 300 |  |  |  | 300
26 | 30" RCP | LF | 69 | 130 | 8970 | -8970 |  |  | 0
27 | 36" Storm Pipe | LF | 62 | 70 | 4340 | -4340 |  |  | 0
28 | 36" End Section | EA | 1 | 1300 | 1300 |  |  |  | 1300
29 | 2' x 2' Grate Inlet Top Replacement | EA | 1 | 1500 | 1500 |  |  |  | 1500
30 | Concrete Flume | SY | 12 | 90 | 1080 |  |  |  | 1080
31 | Concrete Collar | EA | 1 | 1600 | 1600 |  |  |  | 1600
32 | 24" Riprap | SY | 82 | 60 | 4920 |  |  |  | 4920
33 | Traffic Signal Modification-95th Street & Legler/I-435 | LS | 1 | 14000 | 14000 |  |  |  | 14000
34 | Traffic Signal Modification-95th Street & Ridge | LS | 1 | 4000 | 4000 |  |  |  | 4000
35 | 4" Solid White Lane Line (Thermo) | LF | 138 | 2 | 276 |  |  | -276 | 0
35a | 4" Solid White Lane Line (Epoxy) | lf | 138 | 13.75 |  |  |  | 1897.5 | 1897.5
36 | 12" Solid White Crosswalk Line (Thermo) | LF | 175 | 10 | 1750 |  |  | -1750 | 0
36a | 12" solid white Crosswalk Line (Epoxy) | lf | 175 | 16.5 |  |  |  | 2887.5 | 2887.5
37 | 24" Solid White Stop Line (Thermo) | LF | 15 | 13 | 195 |  |  | -195 | 0
37a | 24" solid White Stop Line (Epoxy) | lf | 15 | 22 |  |  |  | 330 | 330
38 | Remove and Reset Existing Signs | EA | 5 | 350 | 1750 |  |  |  | 1750
39 | Traffic Control | LS | 1 | 8000 | 8000 |  |  |  | 8000
40 | 40' Aluminum Pole (w/ 12' Arm & 400w Cobrahead) | EA | 9 | 3500 | 31500 |  |  |  | 31500
41 | 3-1c No. 4 Type USE Distribution Cable | LF | 6900 | 1.75 | 12075 |  |  |  | 12075
42 | Type I Junction Box | EA | 3 | 400 | 1200 |  |  |  | 1200
43 | Street Lighting Conduit - 2" | LF | 1900 | 6 | 11400 |  |  |  | 11400
44 | Relocate Light Pole | EA | 1 | 2000 | 2000 |  |  |  | 2000
0
|  |  |  | TOTAL | 398973.5
45 | Cured in place Pipe 30" CMP | ls | 1 | 30261 |  | 30261 |  |  | 30261
46 | 30" HDPE Storm Pipe | ls | 1 | 4340 |  | 4340 |  |  | 4340
47 | Sodding | ls | 1 | 10124.4 |  |  | 10124.4 |  | 10124.4
0
[6 empty] | 15461 | 9328.9 | 2894 | 426657.4
Work Type Summary
Non-Participating
|  |  |  | Roadway | 12124.4
Participating
|  |  |  | Common Items | 42000
|  |  |  | Roadway | 233463 |  | 426657.4
|  |  |  | Surfacing | 42548
|  |  |  | Bridges | 78522
|  |  |  | Traffic Signals | 18000
|  |  |  | TOTAL | 426657.4